BioPreDyn INTERIM REPORT

Grant Agreement number: 	FP7-KBBE-2011-5-289434

Project acronym: 		BioPreDyn

Project title: 	From Data to Models: New Bioinformatics Methods and Tools for Data-Driven Predictive Dynamic Modeling in Biotechnological Applications

Start date of project:			01.12.2011

End date:				01.12.2014

Period covered: 			from	01.04.2012	to	01.10.2012

Periodic report: 		1st □   2nd X   3rd □   4th □

Period covered: 		from	01.4.2011     to 01.10.2012

Name, title and organisation of the scientific representative of the project's coordinator: Johannes Jaeger, PI, CRG

Project website address: www.biopredyn.eu

### SUMMARY

## Research and Technology

The scientific work within the BioPreDyn consortium is progressing very well, and we are on track for the reporting period (1 April 2012 to 30 September 2012).

One of the imperatives for the project to succeed was to establish a highly interactive network within the consortium, both within the four established focus groups and between them. This has been very successful for defining the benchmark problems and initiating software development, and has already led to a number of collaborative publications. Progress in the specific tasks is 3.2.2.

Deviations:

- The SME Fluxome (FS) went into administration on 28 September 2012. Since this occurred at the end of this reporting time, it did not affect the progress made with FS. FS was an exemplary partner for working together on the project (mainly on WP4 and WP7). The main consequences of this for the project are: i) we will no longer be able to follow up on the resveratrol pathway model, since FS was providing expertise/data for that project; therefore progress on this aspect of our work has not been included here; ii) contributions to Work Package 4 from FS will have to be distributed among the other partners. This should not adversely affect the scientific outcome for reasons outlined below; iii) FS was going to test our software suite as an end-user (WP7). This task cannot be taken over by the rest of the consortium; however, we believe that it could be outsourced to external companies, without an extra cost to the consortium and perhaps providing a greater range of testers than with only one (FS).

- Large scale models in E. coli and yeast: based on discussions among partners at our workshop in June, we decided to shift our main focus in WP4 to yeast, rather than the originally proposed focus on E. coli, since there are better data and models available for yeast, which facilitates the definition of benchmark problems in this organism.

In summary, neither deviation is predicted to have a significant impact on the overall aims and final outcome of the project.

Project objectives for the period

Overview as described in Annex I to the Grant Agreement:

| Delivery (project month | Deliverable number | Deliverable name | Lead Partner | Nature | Dissemination Level |
| --- | --- | --- | --- | --- | --- |
| 12 | 9.5 | 1st Annual Meeting | 1 | O | PP |
| 12 | 9.6 | 1st Short Scientific 6-month Report | 1 | R | PP |

## Work package 1 – Database Integration & Exploitation

(Leader: Partner 6 - di Bernardo)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

3 		EMBL-EBI 		J. Saez

4 		UvA 			J.A. Kaandorp

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

8 		USheff 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

Progress on Task 1.1. and Deliverable 1.1

FTELE.IGM developed a first version of a Matlab tool that enables a user to search for known direct and functional interactions in a query list of biological entities.  The tool implements a set of Web Service API that programmatically accesses public databases in order to search pathways, interactions, and multi-layer networks. The tool returns ranked lists of entities, interactions, neighbors, and pathways containing the searched keywords, which are saved in formats that can be easily imported into popular network analysis tools. EMBL and FTELE.IGEM have established a pipeline to interface from FTELE.IGM’s database using BioMart/BridgeDB. As a future extension, we aim to enrich querying support by providing new sets of API for other resources of biological pathway information, and by obtaining a JAVA implementation of the tool.

Progress on Task 1.2 and Deliverable 1.2

FTELE.IGM developed a first version of a MatLab tool that enables a user to search for known direct and functional interactions in a query list of biological entities (as described in the first Interim report). Towards deliverable D1.2, EBI has contributed to SBML-Qual, in an effort to standardize the exchange of logical models. As part of this effort, EBI also organized the second annual meeting of the Colomoto (Common Logical Modeling Toolbox) community. SBML-qual is now nearly complete.

FTELE.IGM developed a pipeline to normalize and compute in automatic way the differentially expressed genes from two experimental conditions. Currently, they are implementing the BioMart interface for their database. This will be available shortly.

EMBL has co-developed path2models (http://www.ebi.ac.uk/biomodels-main/path2models), which is designed to provide pathway resources in a formatted way; this will be useful for Task T1.2. EMBL was involved in the development of the SBGN standard, for Task 1.1 (and recently published a paper on SBGN standard; LibSBGN, van Iersel et al. Bioinf 2012). A cytoscape plugin for SBGN in Cytoscape, CySBGN, was developed, (http://www.ebi.ac.uk/saezrodriguez/cno/cysbgn/).

Progress on Task 1.3

As a foundation for D1.3 and D1.4, EMBL has developed CellNOpt in R, available as well via a python wrapper and a cytsocape plug-in called cytocopter. These are now available in www.cellnopt.org, with a user interface Cytoscape for  CellNOpt (CytoCopter): http://www.ebi.ac.uk/saezrodriguez/cno/cytocopter.html. Cytocopter could also be applied for D1.5.

Progress on Task 1.5 and Deliverables 1.3, 1.4 and 1.5

CSM is waiting for tools developed in WP1 to be made available for integration; a master document was put on the project intranet in order to gather information about the analysis pipelines to integrate.

To develop standards and tools for integration and comparison of spatial gene expression data within and between species: UvA and CRG will provide spatial expression data and co-ordinate standardization/development efforts.

Spatial gene expression data from the CRG have been made available in the SuperFly database: http://superfly.crg.eu. We are working on extending this database to additional species and developmental gene regulatory networks.

UvA has developed a tool for spatial gene expression data analysis (see also WP2). Our new quantification method produces standardized gene expression profiles from raw or annotated Nematostella data from in situ hybridizations, by measuring the expression intensity along its cell layer. The procedure is based on digital morphologies derived from high-resolution fluorescence pictures. Additionally, complete descriptions of nonsymmetric expression patterns have been constructed by transforming the gene expression images into a three-dimensional representation. For this work, UvA has developed a database containing (published as well as unpublished) in situ hybridizations in the cnidarian Nematostella vectensis. Details about the quantification method can be found  in a submitted manuscript (D. Botman and J.A. Kaandorp, Spatial gene expression quantification: a tool for analysis of in situ hybridization in the sea anemone Nematostella vectensis, manuscript in review).

The approach described under 1.1 (see also WP2) is potentially applicable to many other metazoan model organisms and may also be suitable for processing data from three-dimensional imaging techniques.

Progress on Task 1.6.

To integrate data from metabolomics experiments and flux balance analysis from E. coli, UNIMAN will provide, process, and adapt the relevant data.

Deviations:

UvA: L. Huisman began working on 1 October 2011 but resigned. In August 2012, she was replaced by P. Silva (hired 15 June 2012). Finally, D. Botman is working since 1 February 2012 on the BioPreDyn project.

- Work package 2 – Visualization Tools for Data and Model Building

(Leader: Partner 8 - Lawrence)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

3 		EMBL-EBI 		J. Saez

4 		UvA 			J.A. Kaandorp

8 		USheff 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

USheff has mainly focused on completing the GPLVM implementation in R, for which there is now a working prototype (see Task 2.1 below). The aim will be to integrate this with EMBL-EBI’s re-implementation for DataRail.

UvA has developed a tool for spatial gene expression analysis (as described in WP1, Task 1.5).

EMBL-EBI has been exploring the re-implementation of DataRail in an open source environment, which is essential in order to interface with other partners and, in the future, for integration by Cosmo. The current prototype is based on using R in combination with Cytoscape. USheff has now implemented GPLVM in R, so that integration will be facilitated.

Progress on Task 2.1

The R software GPLVM is now operational. Recently, USheff has been working with Florian Buettner and Fabian Theis at Helmholtz, Munich, to apply the model to their recent ECCB paper. With Jei Hao’s departure (see deviations, below), we are currently discussing the best way to complete this step (since Dr. Hao will continue to collaborate on this, the time she has available within her new job could be a restricting factor). The main final step will be constructing the documentation and examples necessary for releasing the software.

Progress on Task 2.2

There has been a small delay in the integration of the GPLVM software with DataRail, due to the departures of Marijn van Iersel and Jie Hao (see below), but we expect to be able to put the task back on track for completion at M18. The actual route used will depend on the personnel appointed at EMBL and creating an optimal interaction with the newly appointed post-doc (N. Durrande) at USheff.

Progress on Task 2.3

The python GPy library developed by USheff (see also WP3 and WP5) now includes some clustering features for grouping genes with a similar temporal behaviour of gene expression. USheff is developing tools for detecting periodically expressed genes and for extracting their periodic trend. Details of integration of these portions will be discussed at the October 2012 Barcelona meeting.

Deviations: 
USheff: Progress on this work package was delayed by the departure of Jei Hao (who received a position at the Imperial College). Her replacement, Nicholas Durrande, began his contract on 1 September 2012.

Additionally, the PI M. Rattray was recently appointed to a Chair in the Faculty of Life Sciences at the University of Manchester (August 2012). However, we do not foresee that this will hinder the predicted outcome, since the University of Manchester is close to USheff and already contains a BioPreDyn partner site. Dr. Rattray will continue to work closely with USheff on the project, funded where necessary from the USheff node. In fact, he has already had several meetings with new appointee Dr. Durrande. We believe that this move will strengthen links between the two sites without damaging the collaboration between the Rattray and Lawrence groups.

EMBL-EBI: The post-doctoral researcher, Martin van Iersel, left the laboratory in July 2012. His position is expected to be filled in October 2012 (and will most likely be filled by a PhD student and partial support for a staff scientist).

- Work package 3 – Integrated Software Tools for the Modeling Cycle

(Leader: Partner 2 - Banga)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

2 		CSIC 			J. R. Banga

3 		EMBL 			J. Saez

4 		UvA 			J.A. Kaandorp

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

8 		USheff 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

Progress on Task 3.1

USheff has continued working on their Python implementation of a Gaussian process toolkit. These efforts are feeding into this work package as well as WP5 below. The toolkit has now been extended by James Hensman to incorporate clustering of gene expression time series across different replicates (and even species). USheff has submitted a publication at BMC Bioinformatics considering a Drosophila developmental example and a submission to IEEE TPAMI describing the methodology underlying the approach. These ideas come out of fundamental work that has been accepted for publication at the Neural Information Processing Systems conference in December 2012.

Contemporaneously with these developments, PhD student Ricardo Andrade Pacheco has been expanding the toolbox to deal with non-Gaussian data, using sparse Gaussian process methods and the expectation propagation approximation. USheff foresee that this may be useful in augmenting the differential equation model to deal with count data, for example derived from RNA-seq experiments.

FTELE.IGM, in collaboration with USheff, has developed a novel probabilistic model to infer signaling pathways from massive gene expression profiles (both dynamic and steady-state data). Specifically, the method is able to identify modulators (i.e. kinases and phosphatases) that regulate the activity of transcription factors. The approach is based on an innovative application of Multi-Information, and it has been already validated on simulated datasets generated from conditional multivariate Gaussian distributions. Preliminary results obtained on the in silico datasets prompted us to proceed to testing the approach on real gene expression profiles collected from public databases. We are now completing validation of the method on these datasets.

Progress on Task 3.2 and Deliverable D3.2

CSIC has developed a new parameter estimation strategy based on an enhanced scatter search method (eSS, which belongs to the class of stochastic global optimisation algorithms). This technique makes use of diversification (global search) and intensification (local search) methods, and thus can be considered as an advanced hybrid strategy. Currently it can handle non-linear programming (NLP) and, to some extent, mixed-integer nonlinear programming (MINLP) problems. Several innovative mechanisms have been implemented in eSS in order to enhance its efficiency and robustness when solving large-scale optimization problems. CSIC has also implemented another stochastic method for integer programming (combinatorial optimization) based on extensions of the variable neighborhood search (VNS) metaheuristics. These methods were initially implemented in MatLab, and later, in collaboration with EMBL, were implemented in R. CSIC has tested this novel method with benchmark problems, including parameter estimation in large-scale model of microorganisms (see also task 3.3 below).

UNIMAN supplied two benchmark parameter estimation problems that were shared with the CSIC team. These problems are particularly hard parameter estimation problems: a yeast metabolic model with 306 reactions, and a protein translation model for yeast with 56 parameters to be estimated from data from 150 steady states.

The work in this task proceeds as planned and is closely related with deliverable D3.2.

Deliverable D3.2 - Parameter Estimation Tools

CSIC has successfully developed a first version of the parameter estimation tools planned for deliverable D3.2 (due on month 18), and has successfully tested them with several challenging case studies that deal with large-scale E. coli models. These results have been published in BMC Systems Biology. CSIC and EMBL have closely collaborated in the development of a software toolbox, MEIGO, implementing these methods in two popular environments (MatLab and R), with an additional interface with Python. A joint publication describing the toolbox is in preparation.

CRG has performed an extensive study on data requirements for model identification and parameter estimation in the context of the gap gene network of Drosophila. This work has been published in PLoS Computational Biology.

CRG has also developed a new, and very promising, benchmark problem for the BioPreDyn project. We have collected expression data for gap genes at both mRNA and protein levels, which are used to fit a linear delay model simulating translational regulation in this system. The resulting models allow us to estimate parameters such as production, decay, and diffusion rate for gap proteins, as well as translational production delays, in a reliable manner. The estimated parameter values are plausible and can be tested experimentally. Furthermore, this system has several unique advantages for BioPreDyn: (1) Data profiles are of high quality and include information on gene expression variance. (2) Models are simple and feed-forward, and thus amenable to a priori parameter identifiability analysis, uncertainty quantification, and optimal experimental design. (3) The models do not require extensive computation to be solved, which enables us to perform numerically intensive procedures such as bootstrapping for a posteriori identifiability analysis. For these reasons, we are currently using this model as an additional benchmark for the project (in collaboration with CSIC, USheff, and CWI).

Progress on Task 3.3:

CSIC has implemented parallel cooperative metaheuristics that automatically favor the specific optimization strategies developed in Task 3.2 according to the measured current efficiency of each algorithm. The resulting cooperative parallel techniques, named CeSS and CVNS, were initially implemented in Matlab and tested with several large-scale parameter estimation problems, including two challenging problems related with E. coli (this work has been recently published in BMC Systems Biology).

CSIC and EMBL have collaborated on implementing these methods in a software toolbox (MEIGO, metaheuristics for global optimization in bioinformatics and systems biology), which allow users to choose among a wide range of powerful global search methods, taking advantage of parallel high-performance computers. The MEIGO toolbox offers Matlab and R implementations, thus facilitating its use with many existing packages in bioinformatics. EBI has also developed a Python interface to the R version.

MEIGO can be executed in a wide range of computing architectures, ranging from low-cost multi-core PCs to larger and more sophisticated computing clusters. CSIC and EMBL are currently writing a paper describing the toolbox, which will be made available to the scientific community. MEIGO is currently being tested against problems of parameter estimation of dynamical models, as well as structural identification of discrete Boolean models, by EMBL and CSIC.

Similarly to task 3.2, the work in task 3.3 proceeds as planned and is closely related with deliverable D3.2 (Parameter Estimation Tools), due on month 18.

Progress on Task 3.4 and Deliverable D3.4

UvA (in collaboration with the CRG) is currently working on applying multi-objective optimization in the gene regulatory network models which they have developed for Nematostella vectensis (see WP1 and WP2).

CSIC has developed and applied a multi-objective optimization framework to the problem of regulation in metabolic networks. A multi-criteria approach has been used to optimize parameters for the allosteric regulation of enzymes in a model of a metabolic substrate-cycle. This has been carried out by calculating the Pareto set of optimal solutions according to two objectives: the proper direction of flux in a metabolic cycle, and the energetic cost of applying the set of parameters. The results indicate that a final and optimal consensus set of parameters can be obtained, which is an indication of the possible existence of a universal regulation mechanism in metabolic networks. This work has been published in PLoS ONE.

Deliverable D3.4 - Integrated software suite

CSM is waiting for tools developed in WP3 to be available for integration. CSM created one page in the project intranet for each use case identified during the CRG internal workshop (June 2012); the aim is to gather information about those case analyses pipelines. Finally, the pLSA (parallel Lam Simulated Annealing) code was transmitted by CRG to CSM; this code is currently being analyzed by CSM.

Progress on Task 3.5 and deliverable D3.4

CSM has sent every WP participant a short form to be completed, in order to gather information about the different software tools to be included in the software suite (D3.4) and is waiting for all participants to provide this information. The benchmark problems mentioned in Task 3.2 will be used as a foundation to identify a specific suite of methods to be integrated into CSM’s software platform.

CWI has extended the software prototype developed to deal with multi-dimensional independent normally distributed uncertainties to handle correlated and non-normal uncertainties. First results have been obtained on problems from biochemistry and neurodynamics.

The quantification of uncertainty in biochemistry predictions is an important goal in this project. For this reason CWI is also developing a method to look for optimal probability density functions in biochemistry, in order to find the best probabilistic model for the quantities (parameters, initial conditions, inputs). We are applying Polynomial Chaos (PC) expansions for the representation of probabilities density functions and study their utility for the propagation of uncertainty in this context. We are also studying uncertainty quantification of (the delay parameter in) delay equations; application models are for developmental gene regulatory networks (WP6).

UvA has developed a multi-scale model of calcification in scleractinian corals in which the existing knowledge on the contributing sub-processes is integrated within a mathematical framework. UvA has developed a spatial representation of a single coral polyp surrounded by seawater. In this geometry, they simulate the relevant chemical reactions in the external seawater, inside the organism, and at the site of calcification, as well as molecular transport processes, photosynthesis, respiration, and calcium carbonate precipitation. UvA models the spatio-temporal dynamics of the relevant molecular fluxes as a set of coupled reaction-diffusion equations combined with biological transport modelled as Michaelis-Menten and Hill equations. Simulations can be employed to clarify the influence of different individual processes and reaction rates as well as changes in the chemical composition of the surrounding seawater. Details about the model can be found in a publication (C. Cronemberger, L. Huisman, D. Allemand and J.A. Kaandorp, A spatial model of calcification in scleractinian corals, submitted).

This will be highly relevant, since to our knowledge, most computational physiology models are based on ODEs, with only a few examples of (published) computational physiological models that include a spatial component. Potentially, these spatio-temporal physiological models can be coupled with spatio-temporal models of gene regulation and biomechanical models of cells and cell movement and will thus be very useful in multi-scale modeling.

CRG and CSIC have been collaborating on the identifiability of a model of protein production from mRNA on the gap-gene circuit of the Drosophila blastoderm. Spatial expression patterns of mRNA and protein for gap genes (gt, Kr, and kni) are modeled using a simple linear delay model with the objective of investigating whether post-transcriptional regulation is required to explain the quantitative patterns. The model would also allow the determination of production, decay, and diffusion rates, as well as delays, for all three genes. CRG is interested in a sound statistical analysis of the model fit and its identifiability analysis. CSIC is performing a structural identifiability analysis of this model, which is non-trivial due to delay and the presence of a boxcar function representing the shutdown of translation during mitosis. Currently, CSIC is using a non-standard approach based on approximating the boxcar and delayed control by suitable differentiable functions, and then applying the generating series method. Preliminary results indicate that the model parameters are globally identifiable, provided some conditions on the measurements and the delayed control are met. CSIC will double check these results with another approach and will also perform a practical (robust) identifiability analysis.

Progress on Task 3.6

EMBL has developed CellNOptR, a package for the optimization of Boolean logic networks of signaling pathways, based on a previous knowledge network and a set of data upon perturbation of the nodes in the network. This package will be able to make use of the solvers implemented in R and developed in Task 3.3 above.

Deviations:

EMBL-EBI: As mentioned in WP2, the post-doctoral researcher, Martin van Iersel, left the laboratory in July 2012. His position is expected to be filled in October 2012 (and will most likely be filled by a PhD student and partial support for a staff scientist).

CWI: No person months during the first six months were used, since the candidate who accepted the position after the first application round did not take the position at the end of the process. A second application round was opened. Finally, the position was split: one part-time position (0.2 FTE) was filled by a postdoc (Aldemar Torres Valderrama) who moved to CWI on 1 April 2012; a second full-time position was taken up by the candidate chosen in the second application round, Maria Navarro, who was hired on 1 August 2012.

UvA: L. Huisman began working on the project on 1 October 2011 but resigned in August 2012. She was replaced by P. Silva (who started 15 June 2012). Additionally, D. Botman is working as a Master’s student since 1 February 2012 in the BioPreDyn project.

CRG: We have introduced a new benchmark problem to the consortium that deals with translational regulation of gap genes in Drosophila (see above). This is more an addition than a deviation from originally planned work.

Work package 4 – Application: Large-scale Models of Microorganisms

(Leader: Partner 7 - Mendes)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

10		INSIL			K. Mauch

11		FS			J.-M. Mouillon

Progress on Task 4.1

The UNIMAN team has acquired and adapted a reconstruction of the metabolic network of E. coli based on genomic and literature data (iJO1366, doi:10.1038/msb.2011.65). This reconstruction was hindered by the use of non-standard names and by the lack of being annotated with machine-readable methods. Thus, we reassembled the reconstruction as an SBML file enriched with MIRIAM-compliant annotations (which are embedded in the SBML through RDF). All small and macro-molecules are now referenced to an authoritative database, such as UniProt or ChEBI. All molecules and reactions have also been annotated with appropriate publications that contain supporting evidence.

The task performed at FS was to update our current whole-genome S. cerevisiae model in preparation for reconstructing a genome-wide kinetic model of S. cerevisiae. The existing model that was chosen by FS as starting point is the whole-genome metabolic S. cerevisiae reconstruction iN800 (Nookaew et al. 2008 BMC Systems Biology 2:71). The model was updated with a special focus on FS bioprocess, that is, production of polyunsaturated fatty acids in S. cerevisiae.

INSIL has also compiled and transferred proprietary genome-based network models for UNIMAN. The genome-based network models include an annotated E. coli network model (with 1,334 reactions and 942 genes) and a compartmented network model for S. cerevisiae (with 1,174 reactions and 897 genes). The topology of the network models (i.e. substrates, products, and modulators) will be used to set-up large-scale dynamic network models.

Progress on Task 4.2

CSIC started using a genome-scale dynamic model of yeast developed by UNIMAN that considers parameter estimation in a first step, and the global optimization techniques developed by CSIC in WP3. A multi-objective optimization scheme has been adopted, with objective function considering error terms regarding concentrations, fluxes, and (possibly) distance to the initially guessed parameters (the latter can be regarded as a regularization term). Initial analyses have indicated that there are some issues regarding the steady states reached, which are currently being investigated by UNIMAN and CSIC in close collaboration.

UNIMAN also shared with CSIC a model of eukaryotic translation in yeast which is computationally very expensive due to the calculation of 150 steady states (each evaluation  takes ~90 minutes). Therefore, the associated parameter estimation problem is very challenging. CSIC started work on the calibration of this model using  a global optimization method that makes uses of kriging-based surrogate models.

CSIC continued to coordinate the focus group on E. coli benchmark problems. CSIC further contributed by defining classes of benchmark problems based on dynamic models of metabolism of E. coli, namely (i) model calibration of medium and large-scale dynamic models; (ii) identifiablity analysis; and (iii) optimal experimental design.

INSIL developed a large-scale genome-based kinetic E. coli model (with 310 reactions and 317 balanced compounds). The reconstructed kinetic model holds generic rate laws (Michaelis-Menten kinetic approach and linlog kinetics) and represents a Fed-Batch process. Tryptophan was chosen as a main product of the process, while glucose serves as the main substrate. Further substrates include sulfate, ammonium, phosphate, oxygen, and carbon dioxide. Glucose, sulfate, phosphate, and ammonium are fed continuously over the fermentation duration of 24 hours. The applied data set is nominal. The model was delivered to CSIC. The current parameter constellation of the kinetic model restricts the feasibility area of the model. Therefore CSIC and INSIL decided to develop a new method for the stabilization of models to make predictions with large-scale models feasible. INSIL communicated gathered experiences and ideas of possible solutions and the demands for the model with respect to desirable predictions and the aspired predictive quality.

CSIC translated the INSIL model into their Matlab-based AMIGO toolbox in order to carry out further optimization-based analysis, including identifiability and optimal experimental design. CSIC also started to work with the large-scale kinetic E. coli model along the following directions: (i) model stabilization via constrained dynamic optimization, taking into account the requirements outlined by INSIL; and (ii) methods to obtain high-quality predictions (i.e. for a relevant subset of state variables). For the latter case, CSIC has started considering alternatives involving ensemble and consensus modeling methods.

Progress on Task 4.6

INSIL reconstructed two reduced dynamic CHO models that include reference datasets of different sizes and different focuses, and delivered them to CSIC and the CWI to analyze benchmark problems and to further develop their methods. The small metabolic CHO Model (in the following, termed CHO-S) is a reduced version of a large-scale genome-based CHO network model (in the following, CHO-L). The parameters for the model’s kinetics are nominal. The reconstructed kinetic model holds generic rate laws (Michaelis-Menten kinetic approach and linlog kinetics).The compartmented CHO-S model (32 reactions and 30 balanced compounds) represents a batch process and holds the functionalities of product and lactate formation as well as of glucose and amino acid uptake. In contrast to the CHO-S model, the middle-sized CHO model (in the following, CHO-M, encompassing 53 reactions and 54 balanced compounds) adds the following functionalities: production of representative protein, biomass, and RNA. The CHO-M model simulates a Fed-batch process with a constant feed of glucose and the amino acids over time. The annotated kinetics are similar to the CHO-S model (linlog kinetics and irreversible Michaelis-Menten kinetics for the production and biomass synthesis). Adapted to the purpose of developing and testing methods of the modeling cycle, a nominal data set was provided. INSIL is about to finalize the compartmented kinetic CHO-L model. Similar to the E. coli model, the feasibility area of the non-reduced model is limited.

CSIC received the CHO models from INSIL and translated them in a format suitable for their AMIGO toolbox. Similar to the work performed with the E. coli models, CSIC has started working with these models regarding (i) stable model calibration and (ii) high-quality predictions of selected variables of interest.

Thus, CSIC has developed new methods for parameter estimation in large-scale models in the framework of WP3, and has successfully applied these methods to large E. coli models (both static and dynamic) taken from the recent literature. These results have been recently published in BMC Systems Biology. CSIC has started to apply these novel methodologies to the large-scale E. coli and CHO models from INSIL and to the genome-scale yeast model from UNIMAN.

Deviations:

FS: The SME FS went into administration effective on 28 September 2012. This did not impact their progress during this interim; in fact, the FS scientists (J.-M. Mouillon and J. D. Dyekjaer) were highly collaborative and involved actively in the project, and will hopefully be included in the future publications arising from this. The loss of FS will impact WP4 in that it is no longer possible to create the specialized models (e.g. of the reservatol pathway in yeast) that depended on expertise/data from Fluxome. Instead, we will focus on more general whole-cell models of metabolism and regulation, in accordance with the original aims of the project.

E. coli / S. cerevisiae: We propose a shift of focus from large-scale models in E. coli to yeast as our benchmark system. Based on discussions at our workshop in spring, we decided that the availability of data and models was much better suited for our purpose in yeast. This change of focus was approved by the general assembly in June 2012. This will not have any impact on the conceptual and algorithmic aspects of this WP. On the contrary, it will facilitate the development and testing of new methods and tools.

- Work package 5 – Application: Signaling and Regulatory Networks in Cells

(Leader: Partner 3 - Saez-Rodriguez)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

3 		EMBL-EBI 		J. Saez

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

8 		USheff 			N. Lawrence/M. Rattray

10		INSIL			K. Mauch

The first deliverable for WP5 is scheduled to be accomplished in Month 18; thus far, we are in the preparation stage of the work package.

Progress on Task 5.1

FTELE.IGM developed a computational workflow to model the alteration of metabolism caused by loss- or gain-of-function (LoF or GoF) of an enzyme (or transporter), and to predict the metabolites and reactions that are most affected. The computational workflow has been applied to a recent genome-scale metabolic network model of human cell metabolism (hepatocyte). The method is based on Flux Balance Analysis, which is used to derive the “differential fluxes” caused by the LoF or GoF, thus enabling the identification of the metabolites accumulating the most due to the mutation. This approach has been tested by simulating 38 Inborn Errors of Metabolism (IEMs), Mendelian disorders due to the LoF of a single enzyme. In about half of the cases, we correctly identified the metabolites known to accumulate in the blood and urine of IEM patients. This method will be also used towards Task 5.3.

Also for Task 5.1, Task 5.4. , and Deliverable 5.3, INSIL began work on a kinetic model of insulin signaling in hepatocytes. In WP5, INSIL started to model signaling and regulation, with a focus on nutrition-related changes in the metabolic cell phenotype. For this, we constructed a dynamic network model for insulin- and glucagon-induced signaling cascades that lead to regulation at both the enzymatic and gene expression levels of diverse enzymes in central carbon metabolism. The model structure and partly also the dynamics have been deduced from the literature for different signaling pathways (e.g. Koschorreck and Gilles, 20081, Borisov et al., 20092, and Mutalik and Venkatesch, 20053), or from the individual signaling steps. Accordingly, the signal cascades have been set-up with building blocks of signal protein phosphorylation and dephosphorylation steps, as classically described in the literature. The model readout contains the allosteric modification of central metabolic enzymes (that is, their activation or deactivation) as well as gene-regulated enzyme expression. In close collaboration with EMBL-EBI, INSIL has begun to determine an appropriate modeling and identification systematics for signal transduction networks. In a consensus, the two different modeling approaches of deterministic and Boolean logic will be assessed for use in describing the model, which will be performed with suitable benchmark tests. To this end, model approaches have been discussed, and models have been exchanged with EMBL-EBI. Further, for the work on signal transduction networks, INSIL has begun to compile a library of dynamic metabolic CHO network models for performing parameter identification runs, using different modular identification strategies. In order to scale-up the identification problems, INSIL plans to make use of evolutionary strategies/open MPI on the fastest supercomputer in Europe.

Following up this work, INSIL has developed a preliminary kinetic hepatic metabolic model (112 reactions and 103 balanced compounds) that is able to represent the absorptive and post-absorptive state of the hepatocyte. The dynamic model describes the metabolic processes under the influence of the hormones insulin and glucagon. In post-absorptive state (fasting state), glucagon stimulates the hydrolysis of triglycerides in adipocytes resulting in the release of fatty acids into the blood stream. Fatty acids are taken up by hepatocytes and degraded by beta oxidation in the mitochondria. In the absorptive state (fed state), insulin leads to an inhibition of beta oxidation. Fatty acids are synthesized and stored as triglycerides leaving the cell in lipoproteins (VLDLs) being finally stored in adipocytes. The metabolic model reproduces selected dynamics of cellular metabolism (including the glycolysis, gluconeogenesis, pentose phosphate pathway, TCA cycle, oxidative phosphorylation, selective anabolic and catabolic reactions, and lipid metabolism comprising triglyceride synthesis and triglyceride hydrolysis in adipocytes). The adipocyte is modeled as an additional compartment next to the hepatocyte. As representative for all fatty acids, palmitate and oleate were included in the model. Additionally, the model contains cholesterol synthesis, glycogen synthesis and degradation, and glutamate and glutamine metabolism. In the absorptive state, the following pathways are active: glycolysis, glycogen synthesis, fatty acid synthesis, cholesterol synthesis, and triglyceride synthesis. In the post-absorptive state, gluconeogenesis, glycogen degradation, triglyceride hydrolysis in adipocytes, fatty acid uptake, and beta oxidation take place. The model was handed over to EMBL-EBI, who is looking at this network and exploring ways to expand it within a logic model of insulin signaling in hepatocytes.

Progress on Task 5.2

CSIC has begun a close collaboration with EMBL-EBI on the calibration of network models. The PI from CSIC visited EMBL-EBI during July 2012 to enhance this collaboration, a methodological publication is in preparation (see WP3), and application to signaling pathways is undergoing, which will be later connected to the metabolic pathways.

USheff is developing a Gaussian process toolkit in Python that should allow for spatial modeling of gene expression data, based on their published work in Gaussian process modeling for convolution processes. As mentioned in WP3, there have been significant steps forward with our Gaussian process software in Python, particularly with regard to efficiency. These ideas are allowing us to perform large scale clustering of gene expression time series across replicates and species. The new appointee N. Durrande (who replaced J. Hao as the scientist associated with the USheff) has been considering how to extract the periodic nature of noisy, gene-expression time series, even when the samples are not taken uniformly. He has completed a draft report demonstrating that this component can be separated by considering the reproducing kernel Hilbert space of the associated covariance function.

FTELE.IGM has been establishing a new gene regulatory network inference method that will be able to identify gene regulatory pathways and metabolic pathways specifically active in specific tissues and cell types. The method is based on "differential network analysis" and will be used to achieve Tasks 5.1, 5.2, and 5.3. In particular, FTELE.IGM developed a method named DINA (DIfferential Network Analysis), which is able to identify set of genes, whose co-regulation is condition-specific, starting from a collection of condition-specific gene expression profiles (GEPs). DINA is also able to predict which transcription factors (TFs) may be responsible for the pathway condition-specific co-regulation. We derived thirty tissue-specific gene networks in human and identified several metabolic pathways as the most differentially regulated across the tissues. We correctly identified TFs such as nuclear receptors as their main regulators. DINA will be available as an online tool.

Progress on Task 5.4

The focus of the model is to be able to link to the metabolic pathways so as to fulfill D5.4. eventually. Technically, biological switching from one to the other metabolic state was received by changing the capacity of key enzymes depending on the hormone level, which are triggered by two major reactions representing the whole signaling pathway. The major focus in the cooperation with EMBL-EBI lies now in developing and establishing the mathematical modeling framework and appropriate methods for linking signaling and kinetic metabolic models enabling verification of resulting hybrid models.

We have evaluated the availability of suitable experimental data to train CHO signaling models. It appears for the moment that this will not be forthcoming, due to data sharing policy issues. We have therefore decided to focus rather on an alternative model system suggested in the original BioPreDyn proposal, namely hepatocytes, with a particular focus on the insulin signaling pathway. This decision may be reverted at a later stage if the situation on CHO experimental data changes.

- Work package 6 – Application: Developmental Gene Regulatory Networks in Animals

(Leader: Partner 4 - Kaandorp)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

4 		UvA 			J.A. Kaandorp

5 		CWI 			J. Blom

8 		USheff 			N. Lawrence/M. Rattray

Our first deliverable for this package is in month 18. We are still in a preparatory stage for this WP.

Progress on Task 6.1

CRG is developing visualization tools to compare expression patterns across different databases for spatial gene expression in Drosophila (http://superfly.crg.es, http://urchin.spbcas.ru/flyex).

Progress on Task 6.2

UvA has taken the first steps towards setting up a database for spatial gene expression patterns in Nematostella. Specific datasets will be created to model benchmark problems defined by the animal networks focus group. CRG has created a large range of spatial expression datasets in Drosophila and other fly species; these contain quantified data based on colorimetric/fluorescent in situ hybridization and immunofluorescence, which are available for both wild-type and mutant Drosophila backgrounds. These datasets are now being used to begin modeling work in the context of Tasks 6.3 and 6.4.

Progress on Tasks 6.3 and 6.4

The CRG has performed an extensive analysis of data requirements for model fitting and has developed a new benchmark problem for algorithm development and testing (see WP3).

In addition we have initiated model fitting to gap gene expression data in species other than Drosophila. We are currently optimizing the parameters of our algorithms and have initiated preliminary model analyses.

- Work package 7 – Application: Validation of Network Models in Biotechnological Production Processes

(Leader: Partner 11 - Mouillon)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

5 		CWI 			J. Blom

7 		UNIMAN 		P. Mendes

10		INSIL			K. Mauch

11		FS			J.-M. Mouillon

Progress on Task 7.1

UNIMAN provided specifications of its open source software COPASI and how it can be used from the command line or through the Python language.

INSIL has handed over a document with necessary and eligible predictive functionalities of network models to CSIC. Based on the requirements, CSIC will try to further develop their methods. Moreover, INSIL listed common problems in large-scale modeling of biotechnological processes and often occurring challenges in preservation of the model quality.

Progress on Task 7.2

Prototype software for testing: as stated in the previous interim report, COPASI, developed at UNIMAN by P. Mendes and co-workers, has been chosen as prototype software. This decision was verified at the 1st BioPreDyn Workshop in Barcelona, June 2012. Test work is currently on going, with UNIMAN, FS, and CSM involved.

Progress on Task 7.2

CSIC has started the development of optimization-based tools for metabolic engineering of microorganisms. The framework chosen is based on a mixed-integer dynamic optimization formulation. This will allow the development of a software tool for decision support in metabolic engineering. This class of problems will be solved by extending the global optimization methods developed by CSIC in WP3, where great progress has already been made.

Thus, CSIC has already developed several metaheuristic methods for optimization which can be used to solve the metabolic engineering problems considered in WP7 as soon as reliable dynamic models from WP4 are available. These solvers already have parallel implementations which facilitate the scalability of the approach to realistic problems. The solvers will be integrated in the common software platform in the near future.

Positions filled for WP7:

CWI has hired a researcher, Maria Navarro, who started on 1 August 2012.

Deviations:

FS: As mentioned in WP4, FS went into administration effective on 28 September 2012. This had no impact on their progress during this reporting period. The loss of FS will impact WP7, since they were the “end users” and testers for our software suite; however, this task could be taken over by subcontracted companies or, alternatively, by volunteer companies outside the consortium with no additional costs to the consortium.

- Work package 8 – Dissemination, Training, Exploitation

(Leader: Partner 9 - Boix)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

2 		CSIC 			J.R. Banga

A list of dissemination activities can be found in the Annex to this report.

Progress on Task 8.1

CRG management is re-doing the BioPreDyn.eu website, to make it more dynamic.

Progress on Task 8.2

CSM has software development/testing architecture ready to use, but to date has nothing to be committed on it yet.

Progress on Task 8.3

CSM is waiting for tools developed in the project to be made available for integration; a master document was put on the project intranet in order to gather information about the analysis pipelines to integrate. Some code was already given to CSM by CRG (pLSA code).

Progress on Task 8.5

CRG organized the 1st BioPreDyn Workshop: The Systems Biology Modeling Cycle and its Applications, from 11-15 June, at the CRG, Barcelona. This workshop was aimed at post-doctoral fellows and PhD students, focusing on understanding and applying state-of-the-art methods and tools involved in database integration, visualization, and model building. Thirty-five members attended, and eleven members held presentations.  The workshop incorporated lectures (given by the experts within the consortium) and hands-on practical sessions. In addition, since all partners were represented, a day was dedicated to discussing progress in the project and focus groups, and to discussing all issues that were brought up. Evaluation of the workshop by the attendees was positive overall; the opportunity for networking within the consortium was especially appreciated.

Progress on Task 87

As listed in the Annex, members of the consortium have been active in short-term exchanges to other partner laboratories.

- 3.2.3	Project management during the period

The project website is not updated at the time of writing this report, since the platform on which it was based was revealed to be highly difficult to manage. Based on this, the CRG management, led by V. Raker, is in the process of redoing the BioPreDyn.eu website, with a professional . This new website will be live in the middle of October. All members have also signed up for the intranet internal to the project; an additional intranet/wiki site was set up by the SME COSMO, to collect relevant code information from the partners.

The consortium organized a training workshop, held in Barcelona on 11–15 June, during which benchmark problems were discussed and hands-on tutorials were offered by the various partners. We also had the opportunity to discuss any other relevant issues and collaborations, and to introduce new consortium members to the projects and other members. All partners (represented by all PIs and most of the scientists working on the project) attended the workshop. Based on the high attendance level of this workshop, the general assembly decided that an annual meeting (scheduled to be held a few months later) would be relatively redundant. Thus, we would like to substitute the annual meeting with a PI meeting, which will be held in Barcelona on 29 October 2012. The annual meeting will be held 4-6 March in Naples, Italy, 2013. The high level of communication within the project (through teleconferences, personal visits between partners, the project intranet and the intranet/wiki set up by COSMO for communicating codes, group e-mails, etc.) will assure that this lapse of 6 months will not adversely affect the project.

Numerous publications have already arisen from this project (as listed in the Annex), several of which are collaborative.

ANNEX

Partner/project dissemination

Meetings/workshops attended by WP members since 01/04/2012 (*indicates talk/poster with BioPreDyn acknowledged)

*Jaap Kaandorp (UvA) Intl Modeling gene regulation of morphogenesis, International Young Scientists Conference ``High Performance Computing and Simulation’’ April 2012 Amsterdam, Netherlands

Julio Saez-Rodriguez (EMBL-EBI) EFMC course on medicinal Chemistry, April 2012 Leiden, Netherlands

*Pedro Mendes (UNIMAN) presented a seminar entitled “Modelling biochemical networks: What is there to do?” 25 April 2012 University of Edinburgh, Edinburgh

Alex F. Villarde (CSIC) Joint EMBL-EBI-Wellcome Trust Course: In silico Systems Biology 23-27 April 2012 Hinxton, Cambridge, UK

Julio Saez-Rodriguez (EMBL-EBI) Joint EMBL-EBI and Wellcome Trust In Silico Systems Biology 28 April 2012 Hinxton UK

*Jaap Kaandorp (UvA) “Modeling gene regulation of morphogenesis” Turing Centenary Conference and 8th conference on Computability in Europe June 2012 Cambridge, UK

Julio Saez-Rodriguez (EMBL-EBI) Computational Proteomics School June 2012 Munich, Germany

*Jaap Kaandorp (UvA) “Modelling gene regulation of morphogenesis in the sea anemone Nematostella vectensis” The 8th International Conference on Bioinformatics of Genome Regulation and Structure\Systems Biology June 2012 Novosibirsk, Russia

ALL partners: BioPreDyn Workshop: The Systems Biology Modeling Cycle and its Applications 11-15 June 2012 CRG, Barcelona, Spain

*Jaap Kaandorp, (UvA) “A spatial model of calcification in scleractinian corals” 12th International Coral Reef Symposium July 2012 Cairns, Australia

*Pedro Mendes (UNIMAN) “From networks to models – large scale kinetic models of metabolism” 23 August 2012 University of Saarbrucken, Austria

Julio Saez-Rodriguez (EMBL-EBI) Computational Plant Biology August 2012 Sainsbury Institute, Cambridge

Alex F. Villarde (CSIC) XXXIII Jornadas de Automática 5-7 September 2012 Vigo, Spain

*Jaap Kaandorp (UvA) “Complexity of morphogenesis” European Conference on Complex Systems September 2012 Brussels, BE

*Jaap Kaandorp (UvA), poster: "Acropora ‘skeletome’ reveals coral specific proteins and common functional domains in biomineralization", COST action TD0903 workshop 18-20 September 2012 Aarhus, Denmark

Joke Blom (CWI) poster: “BioPreDyn”, The CWI Business day 5 October 2012 and Open Day 6 October 2012 Amsterdam, Netherlands

Submission of publications that acknowledge BioPreDyn (* indicates collaborative publication; bold indicates consortium member)

- Botman, D., and Kaandorp, J.A. Spatial gene expression quantification: a tool for analysis of in situ hybridization in the sea anemone Nematostella vectensis.  Submitted.

- Crombach, A., Cicin-Sain, D., Wotton, K., and Jaeger, J. A. Method for the Fast Processing of Whole Mount in situ Hybridisation Experiments into Gene Expression Domains. PloS One Submitted.

- Crombach, A., Wotton, K.R., Cicin-Sain, D., Ashyraliyev, M., and Jaeger, J. (2012). Efficient reverse-engineering of a developmental gene regulatory network. PLoS computational biology 8, e1002589.

- Cronemberger, C., Huisman, L., Allemand, D., and Kaandorp, J.A. A spatial model of calcification in scleractinian corals. Submitted.

- Eduati, F., De Las Rivas, J., Di Camillo, B., Toffolo, G., and Saez-Rodriguez, J. (2012). Integrating literature-constrained and data-driven inference of signalling networks. Bioinformatics 28, 2311-2317.

- * Egea, J., Henriques, D., Cokelaer, T., Villaverde, A., Banga, J., and Saez-Rodriguez, J. MEIGO: a software suite based on metaheuristics for global optimization in systems biology and bioinformatics.  Manuscript in preparation.

- Gambardella, G., Moretti, M., De Cegli, R., Cardone, L., Peron, A., and di Bernardo, D. Differential Network Analysis for the identification of condition-specific pathway activity and regulation. Bioinformatics Submitted.

- Heavner, B.D., Smallbone, K., Barker, B., Mendes, P., and Walker, L.P. (2012). Yeast 5 - an expanded reconstruction of the Saccharomyces cerevisiae metabolic network. BMC Systems Biology 6, 55.

- Higuera, C., Villaverde, A.F., Banga, J.R., Ross, J., and Moran, F. (2012). Multi-criteria optimization of regulation in metabolic networks. PloS one 7, e41122.

- * Iorio, F., Saez-Rodriguez, J., and Di Bernardo, D. Network based elucidation of drug response: from modulators to targets. Open Network Biology Submitted.

- MacNamara, A., Terfve, C., Henriques, D., Bernabe, B.P., and Saez-Rodriguez, J. (2012). State-time spectrum of signal transduction logic models. Physical biology 9, 045003.

- Pagliarini, R., and di Bernardo, D. A genome-scale modelling approach to study inborn errors of liver metabolsim: towards an in-silico patient. Special Issue J Comp Biol. Submitted.

- Ramos-Silva, P., Zanella-Cleon, I., Huisman, L., Marie, B., Kaandorp, J., Miller, D., and Marin, F. Acropora ‘skeletome’ reveals coral specific proteins and common functional domains in biomineralization. Manuscript in preparation.

- Rybakova, K., Tomaszewska, A., van Mourik, S., Blom, J., Westerhoff, H., Carlberg, C., and Bruggeman, F. Tracing the molecular basis of aberrant transcription in noisy data by using an experiment-based mathematical model. Submitted.

- Smallbone, K., and Stanford, N. (2012). Kinetic modelling of metabolic pathways: Application to serine biosynthesis. Methods in Molecular Biology In Press.

- Terfve, C., and Saez-Rodriguez, J. CellNOptR: a flexible toolkit to train protein signaling net- works to data using multiple logic formalisms. BMC SysBio Submitted.

- van Iersel, M.P., Villeger, A.C., Czauderna, T., Boyd, S.E., Bergmann, F.T., Luna, A., Demir, E., Sorokin, A., Dogrusoz, U., Matsuoka, Y., Funahashi, A., Aladjem, M.I., Mi, H., Moodie, S.L., Kitano, H., Le Novere, N., and Schreiber, F. (2012). Software support for SBGN maps: SBGN-ML and LibSBGN. Bioinformatics 28, 2016-2021.

- Villaverde, A.F., Egea, J.A., and Banga, J.R. (2012). A cooperative strategy for parameter estimation in large scale systems biology models. BMC Systems Biology 6, 75.

Visits of WP members to other BioPreDyn partners and WP teleconferences:

Alex F. Villaverde (CSIC): visit to UNIMAN (Mendes group) 19-20 April 2012

Julio R. Banga (CSIC): research stay at EBI-EMBL (Saez group) 3-30 July 2012

Jean-Marie Mouillon, Jane Dyekjær (FS): visit to UNIMAN (Mendes group) 12-13 September 2012

Bertrand Moreau (CSM) : visit to UNIMAN (Mendes group) 12-13 September 2012

Alex F. Villaverde (CSIC): visit to InSilico Biotechnology (Stuttgart) 25-27 Sept 2012

Bertrand Moreau (CSM) Teleconference Organizer: WP7 Bioproduction software requirements 28 September 2012