FP7-KBBE-2011-5-289434

BioPreDyn

From Data to Models: New Bioinformatics Methods and Tools for Data-Driven Predictive Dynamic Modeling in Biotechnological Applications

Collaborative project

First Interim Report

(October 2011- March 2012)

Period covered: 01/10/11 – 31/03/12			       Date of preparation: 30 March 2012

Start date of project: 01/10/11						         Duration: 36 months

Project coordinator PI name: Johannes Jaeger

Project coordinator organisation name: CRG

Table of Contents

SUMMARY	3

Research and Technology	3

Management, Training and Dissemination	3

Project objectives for the period	4

Work package 1 – Database Integration & Exploitation	5

Work package 2 – Visualisation Tools for Data and Model Building	6

Work package 3 – Integrated Software Tools for the Modelling Cycle	6

Work package 4 – Application: Large-scale Models of Microorganisms	8

Work package 5 – Application: Signaling and Regulatory Networks in Cells	9

Work package 6 – Application: Developmental Gene Regulatory Networks in Animals	10

Work package 7 – Application: Validation of Network Models in Biotechnological Production Processes	11

Work package 8 – Dissemination, Training, Exploitation	11

Work package 9 – Management	12

ANNEX	13

# SUMMARY

## Research and Technology

The scientific work within the BioPreDyn consortium started well, and initial progress was made as expected during the reporting period (1 October 2012 to 31 March 2012). The progress made towards specific tasks and deliverables is described in detail below. No major deviations from the original work plan have occurred to date. Several new collaborations have already been established, especially between the academic partners and the SMEs: CSIC has been coordinating efforts to reverse-engineer metabolic and regulatory models of E. coli with UNIMAN; INSIL has initiated a collaboration on signalling networks in mammalian cell lines with FTELE.IGM; and efforts are being made between UNIMAN and FS to integrate a model of fatty acid biosynthesis into existing metabolic models in yeast. Furthermore, we have defined four focus groups with subsets of partners, based on different model organisms. Each of these has defined specific benchmark problems that exist for the project in the context of (1) E. coli, (2) yeast, (3) mammalian cell lines, or (4) animal gene network models. These focus groups will provide reports describing available data, models, and required methodology for each system. The reports will be evaluated and discussed during the first BioPreDyn workshop scheduled for 11-15 June this year (see below).

## Management, Training, and Dissemination

The coordinator and the management team have created a website (www.biopredyn.eu), organized the kick-off meeting at the CRG in Barcelona (12-13 December 2011), implemented four Focus Groups on defining benchmark models, and organized and held phone conferences for the Focus Groups. The pre-financing for each partner was calculated, communicated, and distributed by the coordinator to the partners within the consortium. A Consortium Agreement has been negotiated and signed by all partners. The first four Deliverables have been achieved. This Interim Report serves to monitor the scientific activities of the BioPreDyn consortium and is designed as a basis for the first BioPreDyn report, due on 1 April 2013. The consortium has organized a training workshop, to be held in Barcelona on 11–15 June, during which the benchmark problems will be discussed. The workshop will also be used to introduce research staff newly hired for this project to the methods and platforms provided by the different partners.

Project objectives for the period

Overview as described in Annex I to the Grant Agreement:

| Delivery (project month | Deliverable number | Deliverable name | Lead Partner | Nature | Dissemination Level |
| --- | --- | --- | --- | --- | --- |
| 6 | 8.1 | Project Website | 1 | R | PU |
| 6 | 9.1 | Consortium Agreement | 1 | O | PP |
| 6 | 9.2 | Quality Assurance Plan | 1 | O | PP |
| 6 | 9.3 | Kick-off Meeting | 1 | R | PP |
| 6 | 9.4 | 1st short scientific 6-month report | 1 | O | PP |

## Work package 1 – Database Integration & Exploitation

(Leader: Partner 6 - di Bernardo)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

3 		EMBL-EBI 		J. Saez

4 		UvA 			J.A. Kaandorp

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

8 		USFD 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

Progress on Task 1.1. and Deliverable 1.1

FTELE.IGM is developing a Relational Database NetBase using PostgreSQL, a powerful open-source object-relational DataBase Management System (DBMS). The database structure conforms to specifics proposed in the MIAME standard to store data and meta-data of Gene Expression Profiles (GEPs). This database integrates an ontology to classify meta-data about tissues and to retrieve tissue-homogenous GEPs.

Progress on Task 1.2 and Deliverable 1.2

FTELE.IGM developed a first version of a MatLab tool that enables a user to search for known direct and functional interactions in a query list of biological entities. The tool returns ranked lists of entities, interactions, neighbors, and pathways containing the searched keywords, which are saved in formats that can be easily imported into popular network analysis tools. In the future, we aim to enrich querying support by providing an API for other resources of biological pathway information and to obtain a JAVA implementation of the tool. Towards deliverable D1.2, EBI has contributed to SBML-Qual, in an effort to standardize the exchange of logical models. As part of this effort, EBI is also organizing the second annual meeting of the Colomoto (Common Logical Modeling Toolbox) community.

Progress on Task 1.3

USheff has begun to implement the Gaussian process latent variable model in a bioconductor through our recent appointment, Jie Hao. One of the PhD students, Arif Rahman, is taking into consideration how to transfer our methodology for combining ChIP connectivity data with gene expression to the Bioconductor. To date, he has been working on the necessary mathematical background.

Progress on Task 1.4

CRG has created a publicly accessible database for gene expression patterns in Drosophila (http://superfly.crg.es). Additionally, CRG is developing scripts (in Python and Perl) that allow for rapid interconversion and combination of spatial gene expression data from diverse sources, such as our own datasets and the FlyEx database (http://urchin.spbcas.ru/FlyEx). UvR has created a document describing spatial gene expression patterns in Nematostella with a focus on axis specification/gastrulation that will serve as the starting point for a publicly-available database.

Progress on Task 1.5 and Deliverable 1.3, 1.4 and 1.5

CSM has requested software information through the appropriate form ("Software basic information template", sent on 27 January 2012); we are still waiting for responses and/or the required information from all of the participants.

Progress on Task 1.6.

UNIMAN has developed a pipeline to incorporate steady-state metabolomic, proteomic, kinetic, and fluxomic data into large-scale models, utilizing flux balance analysis. We will apply the pipeline to E. coli, once the benchmark problems for this organism have been defined.

## Work package 2 – Visualization Tools for Data and Model Building

(Leader: Partner 8 - Lawrence)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

3 		EMBL-EBI 		J. Saez

4 		UvA 			J.A. Kaandorp

8 		USFD 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

We are on schedule for targeting those objectives that have their first deliverables at 18 months. USheff has recently appointed Jie Hao, who has now begun work on implementing the GP-LVM software into the Bioconductor framework; importantly, he has included the possiblity to select inherent dimensionality of the data. We have scheduled a meeting between USFD, CSM, and EMBL-EBI for May, at which we will discuss how to integrate DataRail and the USFD software. Now that a USFD research associate has been appointed, CSM will also look at what needs to be done in terms of integration of DataRail and GP-LVM (Task 2.2).

## Work package 3 – Integrated Software Tools for the Modeling Cycle

(Leader: Partner 2 - Banga)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

2 		CSIC 			J. R. Banga

3 		EMBL 			J. Saez

4 		UvA 			J.A. Kaandorp

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

8 		USFD 			N. Lawrence/M. Rattray

9 		CSM 			E. Boix

Task 3.1: USFD is currently implementing Gaussian process software for network inference with differential equations. This is being done in both R and Python to test the relative benefits of the two platforms.

FTELE.IGM, in collaboration with USFD, is exploring probabilistic models to infer modulators of gene expression (including kinases, phosphatases, and microRNAs) from massive gene expression profiles (both dynamic and steady-state data). We are comparing different modeling approaches, based on multivariate Mutual Information and Independence tests, on simulated datasets generated from conditional multivariate Gaussian distributions.

Task 3.2: CSIC has developed and tested a first prototype of a novel global optimization method for large-scale parameter estimation problems. The method is based on extensions of metaheuristics based on the scatter search framework, paying special attention to local methods that can handle large-scale problems efficiently.

CRG has established minimal data requirements for their simulated annealing algorithm in the context of developmental gene regulatory networks in Drosophila. A manuscript reporting this work is under review at PLoS Comp Biol. Furthermore, we are working on adapting evolution strategies developed by UvA, and the scatter search (SSm) developed by CSIC, into our optimization problems.

The EBI group has been exploring ways to use the methods developed by CSIC, in particular the scatter Search package (SSm) but also the AMIGO toolbox, to parametrize and analyze logic models constructed as differential equations. Furthermore, together with CSIC, they are developing a way to implement the SSm and other optimization routes in an R package.

The benchmark problems and questions for the various organisms have been addressed by the different partners: CRG has chaired a focus group for animal gene network benchmark problems; CSIC has chaired a focus group for E. coli benchmark problems; and UNIMAN has chaired the focus group for S. cerevisiae benchmark problems. These benchmark problems will be used to evaluate methods for task 3.2 (as well as for tasks 3.3–3.5 described below).

Task 3.3: CSIC has developed a first method based on the idea of parallel cooperative metaheuristics. This first version is based on extensions of scatter search and selected local methods. A homogeneous cooperating strategy has been evaluated and implemented into Matlab. The results obtained to date have been very promising, and a first publication with these findings has been submitted.

Task 3.4: CRG and UvA are working on implementing a multi-objective optimization algorithm for inferring developmental gene regulatory networks in animals.

Task 3.5: CSM has sent every WP participant a short form to be completed, in order to gather information about the different software tools to be included in the software suite (D3.4); CSM is still waiting for all the participants to provide this information. The benchmark problems mentioned in Task 3.2 will be used as a foundation to identify a specific suite of methods to be integrated into CSM’s software platform.

CWI has developed and tested a first prototype of uncertainty quantification software for multi-dimensional independent normally distributed uncertainties in Matlab. This will be extended to handle also correlated and non-normal uncertainties.

## Work package 4 – Application: Large-scale Models of Microorganisms

(Leader: Partner 7 - Mendes)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

7 		UNIMAN 		P. Mendes

10		INSIL			K. Mauch

11		FS			J.-M. Mouillon

Task 4.1: The UNIMAN team has acquired and adapted a reconstruction of the metabolic network of E. coli based on genomic and literature data (iJO1366, doi:10.1038/msb.2011.65). This reconstruction was hindered by the use of non-standard names and by the lack of being annotated with machine-readable methods. Thus, we reassembled the reconstruction as an SBML file enriched with MIRIAM-compliant annotations (which are embedded in the SBML through RDF). All small and macro-molecules are now referenced to an authoritative database, such as UniProt or ChEBI. All molecules and reactions have also been annotated with appropriate publications that contain supporting evidence.

The task performed at FS was to update our current whole-genome S. cerevisiae model in preparation for reconstructing a genome-wide kinetic model of S. cerevisiae. The existing model that was chosen by FS as starting point is the whole-genome metabolic S. cerevisiae reconstruction iN800 (Nookaew et al. 2008 BMC Systems Biology 2:71). The model was updated with a special focus on FS bioprocess, that is, production of polyunsaturated fatty acids in S. cerevisiae.

INSIL has also compiled and transferred proprietary genome-based network models for UNIMAN. The genome-based network models include an annotated E. coli network model (with 1,334 reactions and 942 genes) and a compartmented network model for S. cerevisiae (with 1,174 reactions and 897 genes). The topology of the network models (i.e. substrates, products, and modulators) will be used to set-up large-scale dynamic network models.

Task 4.2: The UNIMAN team is in the final stages of constructing a kinetic model for S. cerevisiae that contains 278 reactions with 268 chemical species. The model is strictly thermodynamically balanced and uses a generic-rate law (convenience kinetics; doi:10.1186/1742-4682-3-41). The model is being parametrized by estimating the values of the parameters against a set of experimentally-determined fluxes and concentrations. This model will also work as a benchmark for comparing algorithms of parameter estimation and identifiability analysis. The UNIMAN team is also building a yeast kinetic model with detailed kinetics, based on parameter values that were experimentally determined in-house (from in vitro experiments) and on current literature (Sabio-RK).

CSIC has chaired the focus group on E. coli benchmark problems. CSIC has contributed to defining a benchmark problem with a dynamic model of the central carbon metabolism of E. coli. This benchmark is being used to evaluate methods for tasks 3.2.1 and 3.3.1

Tasks 4.3 and 4.4: FTELE.IGM is contributing to Tasks 4.3 and 4.4 by reverse-engineering a genome-wide gene regulatory network from a gene expression profile in E. coli and thereafter linking it to the metabolic network. We are currently developing a set of methodological tools to reverse-engineer the network using multivariate mutual information techniques from gene expression profiles.

## Work package 5 – Application: Signaling and Regulatory Networks in Cells

(Leader: Partner 3 - Saez-Rodriguez)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

3 		EMBL-EBI 		J. Saez

5 		CWI 			J. Blom

6 		FTELE.IGM 		D. di Bernardo

8 		USFD 			N. Lawrence/M. Rattray

10		INSIL			K. Mauch

The first deliverable for WP5 is scheduled to be accomplished in Month 18; thus far, we are in the preparation stage of the work package.

For Deliverable 5.2, EBI has started to work on a logic model of insulin signaling in hepatocytes.

For Deliverable 5.3, INSIL has started to work on a kinetic model of insulin signaling in hepatocytes. In WP5, INSIL started to model signaling and regulation, with a focus on nutrition-related changes in the metabolic cell phenotype. For this, we constructed a dynamic network model for insulin- and glucagon-induced signaling cascades that lead to regulation at both the enzymatic and gene expression levels of diverse enzymes in central carbon metabolism. The model structure and partly also the dynamics have been deduced from the literature for different signaling pathways (e.g. Koschorreck and Gilles, 20081, Borisov et al., 20092, and Mutalik and Venkatesch, 20053), or from the individual signaling steps. Accordingly, the signal cascades have been set-up with building blocks of signal protein phosphorylation and dephosphorylation steps, as classically described in the literature. The model readout contains the allosteric modification of central metabolic enzymes (that is, their activation or deactivation) as well as gene-regulated enzyme expression. In close collaboration with EMBL-EBI, INSIL has begun to determine an appropriate modeling and identification systematics for signal transduction networks. In a consensus, the two different modeling approaches of deterministic and Boolean logic will be assessed for use in describing the model, which will be performed with suitable benchmark tests. To this end, model approaches have been discussed, and models have been exchanged with EMBL-EBI. Further, for the work on signal transduction networks, INSIL has begun to compile a library of dynamic metabolic CHO network models for performing parameter identification runs, using different modular identification strategies. In order to scale-up the identification problems, INSIL plans to make use of evolutionary strategies/open MPI on the fastest supercomputer in Europe.

1.	Koschorreck, M. & Gilles, E. D. Mathematical modeling and analysis of insulin clearance in vivo. BMC Syst Biol 2, 43 (2008).

2.	Borisov, N. et al. Systems-level interactions between insulin-EGF networks amplify mitogenic signaling. Mol. Syst. Biol. 5, 256 (2009).

3.	Mutalik, V. K. & Venkatesh, K. V. Quantification of the glycogen cascade system: the ultrasensitive responses of liver glycogen synthase and muscle phosphorylase are due to distinctive regulatory designs. Theor Biol Med Model 2, 19 (2005).

We have established a framework for comparison of the two model formalisms as a cooperation between INSIL and EBI.

Task 5.2: CSIC has begun a close collaboration with EBI on the calibration of network models. The PI from CSIC will visit EBI during July 2012 to enhance this collaboration.

USFD is developing a Gaussian process toolkit in Python that should allow for spatial modeling of gene expression data, based on their published work in Gaussian process modeling for convolution processes.

FTELE.IGM has been establishing a new gene regulatory network inference method that will be able to identify gene regulatory pathways and metabolic pathways specifically active in specific tissues and cell types. The method is based on "differential network analysis" and will be used to achieve tasks 5.1, 5.2 and 5.3.

We have evaluated the availability of suitable experimental data to train CHO signaling models. It appears for the moment that this will not be forthcoming, due to data sharing policy issues. We have therefore decided to focus rather on an alternative model system suggested in the original BioPreDyn proposal, namely hepatocytes, with a particular focus on the insulin signaling pathway. This decision may be reverted at a later stage if the situation on CHO experimental data changes.

## Work package 6 – Application: Developmental Gene Regulatory Networks in Animals

(Leader: Partner 4 - Kaandorp)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

4 		UvA 			J.A. Kaandorp

5 		CWI 			J. Blom

8 		USFD 			N. Lawrence/M. Rattray

Our first deliverable for this package is in month 18. We are still in a preparatory stage for this WP.

Task 6.1: CRG is developing visualization tools to compare expression patterns across different databases for spatial gene expression in Drosophila (http://superfly.crg.es, http://urchin.spbcas.ru/flyex).

Task 6.2: UvA has taken first steps towards setting up a database for spatial gene expression patterns in Nematostella. Specific datasets will be created to model benchmark problems defined by the animal networks focus group. CRG has created a large range of spatial expression datasets in Drosophila and other fly species; these contain quantified data based on colorimetric/fluorescent in situ hybridization and immunofluorescence, which are available for both wild-type and mutant Drosophila backgrounds. These datasets are now being used to begin modeling work in the context of tasks 6.3 and 6.4.

## Work package 7 – Application: Validation of Network Models in Biotechnological Production Processes

(Leader: Partner 11 - Mouillon)

Main contributors:

Number  	Partner short name 	 P.I.

2 		CSIC 			J. R. Banga

5 		CWI 			J. Blom

7 		UNIMAN 		P. Mendes

10		INSIL			K. Mauch

11		FS			J.-M. Mouillon

Task 7.1: FS has provided a "wish list" for the development of the software package by the partners.

FS specifications for software functionality and GUI: a list of desirable functionalities and user interface selections has been proposed by FS and shared with the other WP investigators. This was to be completed by month 3, and therefore, this task has met the deadline.

Task 7.2: Prototype software for testing: as agreed on the BioPreDyn kick-off meeting (Barcelona, December 2011), COPASI software developed by Pedro Mendes and coworkers (UNIMAN) was chosen as prototype software. This work is currently running according to the predetermined schedule for deliverables.

Task 7.3: CSIC has discussed with partners the first "wish list" received from FS, in which they clarify the focus on metabolic engineering of the project to provide them with suitable tools in the future. INSIL provided topology for the large-scale network models (e.g. E. coli and S. cerevisiae) to UNIMAN.

## Work package 8 – Dissemination, Training, Exploitation

(Leader: Partner 9 - Boix)

Main contributors:

Number  	Partner short name 	 P.I.

1 		CRG 			J. Jaeger

2 		CSIC 			J.R. Banga

D8.2: Software development will be operational by the end of March 2012.

D8.3: Currently, we are waiting for all participants to provide information about the tools to be integrated as well as for detailed descriptions of the SB protocols / workflows that should be integrated. Impact on other tasks: none.

D8.4: There is a talk planned for the Barcelona meeting (15 June 2012).

D8.6: The first training workshop with BioPreDyn participants will take place in June 2012 at the CRG.

A list of dissemination activities can be found in the Annex to this report.

## Work package 9 – Management

(Leader: Partner 1 - Jaeger)

To date, the coordinator and the management team have created a website (www.biopredyn.eu) and the project intranet, set up dedicated mailing lists, organized the kick-off meeting at the CRG in Barcelona (12-13 December 2011), implemented four Focus Groups on benchmark model definitions, and arranged and participated in phone conferences for the Focus Groups. The pre-financing for each partner has been calculated, and the results have been communicated and distributed by Partner 1 within the consortium. A Consortium Agreement has been negotiated and signed by all partners. The first four Deliverables were achieved. This Interim Report serves to monitoring the scientific activities of the BioPreDyn consortium and is designed as a basis for the first BioPreDyn report, due on 1 April 2013.

# ANNEX

1. Dissemination

(A) Project/Partner Meetings attended by WP members since 1 October 2011

All project partners attended the BioPreDyn Kickoff Meeting, Barcelona (12-13 December 2011)

(Note that the following names have been abbreviated below: MvI, Martijn van Iersel; JSR, Julio Saez-Rodriguez; KM,  Klaus Mauch; JB, Joachim Bucher; DdB, Diego di Bernardo; GG, Genarro Gambella; RP, Roberto Pagliarini)

- MvI, KM, JB: attended meeting at Insilico, Stuttgart, 8 March 2012

(B) Presentations with acknowledgment to BioPreDyn at open

Conferences/Workshops since 1 October 2011

CRG:

J. Jaeger (March 2012) Contributed Platform Talk, Drosophila Research Conference, Chicago, USA

J. Jaeger (December 2011) Invited Seminar, Systems Biology Department, University of Exeter, UK

UvA:

J.A. Kaandorp. Oral presention: "Cell-based modeling of gastrulation of Nematostella vectensis and Acropora millepora—searching for Eve Basal metazoans and the evolution of multicellular complexity", Evangelische Akademie Tutzing, Germany (October 2011)

Botman, D., Kaandorp, J.A. and Sloot, P. Poster entitled: "An integrated approach to infer the gene network in early development of the cnidarian Nematostella venctensis. Searching for Eve: Basal metazoans and the evolution of multicellular complexity." Tutzing, Germany (October 2011)

J.A. Kaandorp, L. Huisman and C. Cronemberger. Oral presentation: "Multi-scale modeling of calcification in scleractinian corals", Oceanographic Institute, Monaco (February 2012)

CSIC:

J. R. Banga. Oral presentation: "Identification, analysis and control of biological systems via global optimization", Invited Seminar Speaker, Auditori Antoni Caparrós, Parc Científic Barcelona, Spain (17 November 2011)

J. R. Banga. Oral presentation: "Optimality principles in computational systems biology", Invited Seminar, Invited Seminar Speaker at Multidisciplinary Seminar Program, ETSEQ, Universitat Rovira i Virgili, Tarragona, Spain (18 November 2011)

EMBL-EBI:

JSR gave the following talks:

- Invited talk at the RECOMB/DREAM/RICCI conference, Barcelona, Spain (14-19 October 2011)

- Invited talk at the NCRI (National Cancer Conference), Liverpool, Great Britain (7 November 2011)

- Invited talk at Lorenz workshop, Leiden, the Netherlands (13 February 2012)

MvI. Poster entitled: "Integration and Interoperability for logic modeling tools", Lorenz workshop, Leiden, the Netherlands (13 February 2012)

MvI. Poster entitled: "Visualization for logic modeling tools", Vizbi conference, Heidelberg, Germany (6-8 March 2012)

JSR: Oral presentation, as invited speaker, at the RECOMB/DREAM/RICCI conference, Barcelona, Spain (14-19 October 2011)

JSR. Oral presentation, as invited speaker, at the NCRI (National Cancer Conference), Liverpool, Great Britain (7 November 2011)

JSR. Oral presentation, as invited speaker, at Lorenz workshop, Leiden, the Netherlands (13 February 2012)

CWI, UNIMAN, FS, and INSIL:

No conferences or workshops with acknowledgement to BioPreDyn during this period.

(C) Submission of manuscripts/publications in which BioPreDyn is acknowledged since 1 October 2011

CRG:

Crombach, A., Wotton, K. R., Cicin-Sain, D., Ashyraliyev, M. & Jaeger, J. Efficient reverse-engineering of a developmental gene regulatory network. PLoS Comp Biol (in review).

UvA:

Kaandorp, J.A., Botman, D., Tamulonis, C., & Dries, R. Multi-scale modeling of gene regulation of morphogenesis, Computability in Europe 2012 lecture notes (accepted)

CSIC:

Villaverde, A.F., Egea, J.A., & Banga, J.R. A cooperative strategy for parameter estimation in large scale systems biology models. Submitted, under review.

EMBL-EBI:

Terfve C. et al. CellNOptR: a flexible pipeline to model protein signalling networks trained to data using various logic formalisms. Submitted to Bioinformatics

MacNamara A. et al. State-time spectrum of signal transduction logic models. Submitted to Physical Biology

FS:

Press release: "Fluxome to strengthen its technology platform through extensive European modeling tool project" (31 January 2012) http://www.fluxome.com/news/news/fluxome-to-strengthen-its-technology-platform-through-extensive-european-modeling-tool-project.aspx

INSIL:

Press release: "New Modeling Platform for Industrial Bioproduction" (26 January 2012). Link: http://www.insilico-biotechnology.com/new_modeling_platform_for_industrial_bioproduction

2. Use of Resources

(A) Use of resources, in particular highlighting and explaining deviations between actual and planned person-months per work package and per beneficiary in Annex 1 (Description of Work)

WP1: We have used 13 person-months in total, as predicted in the work plan.

WP3:

CSIC has hired a researcher (Alejandro F. Villaverde), who started on 1 January 2012, without deviations. The person months of own personnel have been used as planned, without  deviations.

FTELE.IGM: 2 person months, without deviations.

EMBL: a postdoc (Martijn van Iersel) started to work on the project on January 2012 (3 person-months until March 2012).

UNIMAN hired a researcher (Kieran Smallbone) who started on 1 November 2011, without  deviations. The person months of own personnel have been used as planned without deviations.

CSM – An engineer, Bertrand Moreau, was hired on 4 January 2012, without deviation.

CWI deviation: no person months this period. The candidate who accepted the position after the first application round finally did not take the position. The second application round is now in the final stage.

CWI action: The position will be split; one part-time position (uncertainty quantification) will be filled by a postdoc who moves to CWI on 1 April 2012; the second, full-time position will be taken up by the candidate chosen in the second application round.

WP4:

CSIC has hired a researcher (Alejandro F. Villaverde) who started on 1 January 2012, without deviations. The person months of own personnel have been used as planned, without  deviations.

UNIMAN hired a researcher (Kieran Smallbone) who started on 1 November 2011, without deviations. The person months of own personnel have been used as planned, without deviations

FS: FTE was allocated according to the defined plan (6 person months).

CWI: has not yet hired personnel

FTELE.IGM has allocated 1 person month as planned.

WP5:

CSIC has hired a researcher (Alejandro F. Villaverde) who started on 1 January 2012, without deviations. The person months of own personnel have been used as planned, without deviations

EMBL has hired a researcher (Martijn van Iersel) who started to work at BioPreDyn on 1 January 2012, without deviations. The person months of own personnel have been used as planned, without deviations

WP6:

L. Huisman has been working since 1 October 2011, and D. Botman since 1 February 2012, on the BioPredyn project.

CRG: A postdoc (A. Crombach) was hired on 20 March 2012 to work on the project. A programmer (D. Cicin-Sain) who is working on the project has already joined our group but will be paid from another project until his current contract terminates. He will be paid from the BioPreDyn project from 1 December 2012 but has already started working on issues related to BioPreDyn.

WP7:

CSIC hired a researcher (Alejandro F. Villaverde) who started on 1 January 2012, without deviations. The person-months of own personnel have been used as planned, without deviations.

UNIMAN hired a researcher (Kieran Smallbone) who started on 1 November 2011, without deviations. The person months of own personnel have been used as planned, without deviations.

FS hired a researcher (Jane Dannow Dyekjær) who started on 1 December 2011, without deviations. The person months of own personnel have been used as planned, without deviations.

INSIL The person months of own personnel have been used as planned, without deviations