First Interim Report

Reporting Period: 1 October 2011 - 31 March 2012

Workpackage: WP3

Work package title:  Integrated Software Tools for the Modelling Cycle

WP leader: CSIC (partner no. 2)

To be completed commonly  BY ALL WP PARTNERS

1. Dissemination

1. Project/Partner Meetings attended by WP members since 01/10/2011

<Insert the meetings here>

CSIC: three members of the team (Julio R. Banga, Eva Balsa, Alejandro Villaverde) attended the kick-off meeting at CRG (Barcelona) on 12-13 December 2011.

FTELE.IGM Diego di Bernardo – Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011

EMBL: Julio Saez-Rodríguez – Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011

CWI: Joke Blom – Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011

USFD: N. Lawrence – Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011

UNIMAN: Pedro Mendes, Kieran Smallbone - Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011.

CSM: Eric Boix – Biopredyn Kickoff Meeting, Barcelona, 12-13 December 2011

2. Presentations with acknowledgment to BioPreDyn at open

Conferences/Workshops since 01/10/2011

<Insert your presentations (oral or poster) here>

CSIC: Julio R. Banga gave two invited talks related with the ongoing work in BioPreDyn:

- "Identification, analysis and control of biological systems via global optimization". Invited Seminar at Auditori Antoni Caparrós - Parc Científic Barcelona, 17-Nov-2011

- "Optimality principles in computational systems biology". Invited seminar.  Multidisciplinary Seminar Program, ETSEQ, Universitat Rovira i Virgili, Tarragona, 18-Nov-2011

EMBL: Julio Saez-Rodríguez gave the following talks:

- Invited talk at the RECOMB/DREAM/RICCI conference, Barcelona 14-19 October 2011

- Invited talk at the NCRI (National Cancer Conference), Liverpool 7 November 2011

- Invited talk at Lorenz workshop, Leiden, the Netherlands, February 13 2012

3. Submission of Papers/Publications with acknowledgment to BioPreDyn

since 01/10/2011

<Insert your papers here>

CSIC:

Alejandro F Villaverde, Jose A Egea and Julio R Banga (2012) A cooperative strategy for parameter estimation in large scale systems biology models. Submitted, under review.

EMBL:

Terfve et al., CellNOptR : a flexible pipeline to model protein signalling networks trained to data using various logic formalisms. Submitted to Bioinformatics

MacNamara et al., State-time spectrum of signal transduction logic models. Submitted to Physical Biology

2. Status of work

PIs being involved and having to comment on this WP:

Number  	Partner short name 	 P.I.			Postdoc/other

1 		CRG 			J. Jaeger		Anton Crombach, postdoc

Damjan Cicin-Sain,programmer

2 		CSIC 			J. R. Banga		Alex F. Villaverde

3 		EMBL 			J. Saez			Martijn van Iersel

4 		UvA 			J.A. Kaandorp		Lotte Huisman PhD

Daniel Botman PhD

5 		CWI 			J. Blom			T.B.Appointed (PostDoc)

6 		FTELE.IGM 		D. di Bernardo		G. Gambardella (PhD)

Luca Cardone (PostDoc)

7 		UNIMAN 		P. Mendes		Kieran Smallbone

8 		USFD 			N.Lawrence/M.Rattray	R.  Andrade Pacheco (PhD)

T.B.Appointed (PostDoc)

9 		CSM 			E. Boix			Thomas Lacroix (CTO),

Bertrand Moreau (Jan. 2012)

6. A. Summary of progress towards objectives: current situation, achievements, established cooperational work within the consortium; highlight significant results (Annex I including the table of Deliverables came with this template)

<Insert your progress here>

Task 3.1- USFD is currently implementing Gaussian process software for network inference with differential equations. This is being done in both R and python to test the relative benefits of the two platforms.

Task 3.1.1- FTELE.IGM, in collaboration with USFD is exploring probabilistic models to infer modulators of gene expression (i.e. kinases,  phosphatases, microRNA, etc.) from massive gene expression profiles  (both dynamic and steady-state data). We are comparing different modeling approaches, based on multivariate Mutual Information and Independence tests on simulated dataset generated from conditional multivariate Gaussian distributions.

Task 3.2.1- CSIC has developed and tested a first prototype of a novel global optimization method for large-scale parameter estimation problems. The method is based on extensions of metaheuristics based on the scatter search framework, paying special attention to local methods which can handle large-scale problems in an efficient way.

The EMBL group has been exploring the use of the methods developed by CSIC, in particular the scatter Search package (SSm) but also the AMIGO toolbox, to parametrize and analyse logic models constructed as differential equations. Furthermore, together with CSIC, an implementation of the SSm and other optimization routied  in an R  package is in development.

Task 3.2.2- CSIC has chaired the focus group on E. coli benchmark problems. CSIC has contributed with a benchmark problem based on a dynamic model of the central carbon metabolism of E. coli. This benchmark is being used to evaluate methods for task 3.2.1 and

UNIMAN has chaired the focus group on S. cerevisiae benchmark problems. UNIMAN is finalizing a benchmark problem based on a medium-scale kinetic model of the metabolism of S. cerevisiae. This benchmark will be used to evaluate methods for tasks 3.2.

Task 3.3.1- CSIC has developed a first method based on the idea of parallel cooperative metaheuristics. This first version is based on extensions of scatter search and selected local methods. An homogeneous cooperating strategy has been evaluated so far, and implemented in Matlab. The results have been very promising and a first publication with these findings has been submitted

Task 3.5 – CSM has sent a short form to be filled by every WP participant in order to gather information about the different software tools to be included in the software suite (D3.4); CSM is still waiting for all the participants to provide this information.

Task 3.5.2- CWI has developed and tested a first prototype of uncertainty quantification software for multi-dimensional independent normally distributed uncertainties in Matlab. This will be extended to handle also correlated and non-normal uncertainties.

B. Reasons for deviations from Annex I (Description of Work) and their impact on other tasks as well as on available resources and planning, if applicable

<Insert your deviations here>

C. Reasons for failing to achieve critical objectives and/or not being on schedule and explanation of the impact on other tasks as well as on available resources and planning

<Insert your failures here>

D. Use of resources, in particular highlighting and explaining deviations between actual and planned person-months per work package and per beneficiary in Annex 1 (Description of Work)

<Insert your use of resources here>

CSIC has hired a researcher (Alejandro F. Villaverde) who started on 1-Jan-2012 – no devitiations. The person-months of own personnel have been used as planned - no deviations

FTELE.IGM: 2 person/months – no deviations

EMBL: a postdoc (Martijn van Iersel) started to work on the project on January 2012 (3 person-months until March 2012).

UNIMAN hired a researcher (Kieran Smallbone) who started on 1-Nov-2011 – no deviations. The person-months of own personnel have been used as planned - no deviations

CSM – 1 engineer (Bertrand Moreau) hired on January 4th 2012 – no deviation.

CWI deviation: no person-months this period. The candidate that accepted the position after the first application round finally did not take up the position. The second application round is now in the final stage.

CWI action: The position will be split, one part-time position (uncertainty quantification) will be filled by a postdoc who moves to CWI April 1; the second – full-time – position will be taken up by the candidate chosen in the second application round.

E. Propose corrective actions, if applicable

<Insert your corrective actions here>