ACTION POINTS

WP1: Coordination and Communication

- IRDiRC - GEUVADIS will be involved in the EC-NIH coordination before projects are funded. Link with other initiatives (ENGAGE, ESGI, TECHGENE, etc.) to be enhanced

- Link with Illumina and Life Technologies (Spike-in controls, data compression with EBI) research activities to be enhanced on specific projects

- Potential link with OMIM to be defined. OMIM will pay attention to GEUVADIS genetic findings

- Partners should highlight GEUVADIS more in their genomics medicine publications, individual or collaborative

WP2: Quality Control

- Matthias (Uppsala) will reshape and simplify the survey he prepared and send it around to partners, and also to other projects members like ICGC partners that are part of GEUVADIS

- Recommendations from ENCODE and READNA to be explored

- Data collected before next year, and recommendations to be defined - 2013

- Terry will collect information on existing standardisation projects on sequencing technologies for diagnosis in the GEUVADIS participating countries

WP3: Data storage

- Submission of all GEUVADIS produced sequencing data to EGA

- Define a Data Access Committee

- All info on EGA already available on intranet (Natalja)

WP4: RNAseq

- HapMap samples project:

  - Deadline for submission of fastq files to EBI remains the same, Feb 15 2012

  - Tuuli will try to push Illumina to send the kits asap

  - If kits delivery late, deadline will be adapted

- Data analysis plan defined by Tuuli, (link with 1KGP analysis group) working group registered on the mailing list. Wiki in place

- March: low level data processing, Oct. 2012: paper submission. Other projects for RNAseq: Chronic Inflammatory Disorders, Parkinson’s Disease brain samples

WP5: Exome seq

- Mental Retardation, Parkinson’s Disease, Chronic Inflammatory Disorders (possible participation of Uppsala and Geneva - with T-cells controls dataset) and Fibromyalgia projects to follow up

- Publication of general findings of GEUVADIS investigators exome data on incidental findings and other data that not relevant for the specific exome-seq projects

- Common GEUVADIS database of already generated data (estimated over 3,000 exomes) Tim (Munich) will coordinate

WP6: ELSI

- ELSI questionnaires analysis publication

- New questionnaire for clinicians: how do they decide to send the patient to get a genetic test

- GEUVADIS Informed Consent template form in place for ongoing and future projects

- DTC: write a position paper and initiate creation of an information platform for the General Public on how to use a DTC and interpret DTC results

WP7: Dissemination and training

Explore participation of Life technologies and Illumina to the different workshops.

New Meetings and workshops:

- Joris Veltman: September 15-18, 2012. Focused, very practical course on routines for variant detection and prioritization of potentially pathogenic

- Summer 2012: Course on RNAseq, Marc Sultan

- Next GEUVADIS annual meeting in Santiago de Compostela